## Front Sheet
AI Risk Register
Sample — AI Governance Starter Edition
Black Chili ¦ blackchili.co.uk
Organisation | [Your Organisation Name]
Document | AI Management System Risk Register
Version | Sample / Free Edition
Prepared by | Black Chili Limited
About this sample
This register contains 15 pre-populated AI risks across the key governance,
data, supplier, technical, and compliance categories that affect most UK
organisations using AI tools.
It is designed to give you a starting point and a sense of what a structured
AI risk register looks like in practice. The full register — 48 risks, residual
scoring, ISO 42001 mapping, and treatment plans — is delivered as part of
Black Chili's AI Governance & Guardrails Design service.
To discuss a full engagement: hello@blackchili.co.uk

## Risk Register
AI Management System Risk Register — Sample Edition ¦ blackchili.co.uk
RISK IDENTIFICATION | [7 empty] | INHERENT RISK |  |  |  |  | TREATMENT
Ref | External Ref | Risk Description | Asset | Threat | Outcome / Consequence | CIA | Existing Control | Impact | Likelihood | Risk Score | Risk Rating | Risk Owner | Treatment | Treatment Plan
1 | AI-GOV-001 | No AI acceptable use policy in place | AI Governance Framework | Ungoverned AI use | Data breaches, regulatory exposure, reputational damage from inappropriate AI use | CIA | None in place | 4 | 5 | 20 | Critical | [AI Policy Owner] | Risk Reduction | Develop and publish AI Acceptable Use Policy. Communicate to all staff.
2 | AI-GOV-002 | No defined AI governance framework or ownership structure | AI Governance | Accountability gap | AI risks not identified or managed. Policy breaches not acted on. Regulatory exposure. | CIA | None in place | 4 | 4 | 16 | Critical | [AI Policy Owner] | Risk Reduction | Define AI governance framework. Assign AI Policy Owner. Establish oversight cadence.
3 | AI-SHA-001 | Staff using personal or consumer AI accounts for work purposes | Staff AI Usage | Data exfiltration via consumer AI tools | Sensitive data submitted to tools with no enterprise protections. Data used to train models. | CIA | None in place | 4 | 5 | 20 | Critical | [AI Policy Owner] | Risk Reduction | Publish AUP prohibiting personal AI accounts for work. Implement technical blocking.
4 | AI-SHA-003 | Shadow AI use not detectable — no visibility of unsanctioned tool access | AI Monitoring | Undetected AI misuse | Policy breaches go undetected. Risks not identified until after damage occurs. | CIA | General web filtering may exist but AI categories not monitored | 4 | 4 | 16 | Critical | [AI Policy Owner] | Risk Reduction | Implement logging of AI tool category access. Review blocked and allowed access regularly.
5 | AI-DAT-001 | Personal data submitted to AI tools without assessment or authorisation | Personal Data | GDPR breach via AI tool | GDPR breach. ICO investigation. Reputational damage. Potential fines. | CIA | GDPR policy exists but does not specifically address AI tools | 5 | 4 | 20 | Critical | [AI Policy Owner] | Risk Reduction | AUP to prohibit personal data in AI tools without approval. Assess each tool for GDPR compliance.
6 | AI-DAT-002 | Client or commercially sensitive data submitted to AI tools | Client / Commercial Data | Confidentiality breach | Client data exposed to supplier. Contractual breach. Loss of client trust. | CA | None specific to AI | 5 | 4 | 20 | Critical | [AI Policy Owner] | Risk Reduction | AUP prohibition on client data. DLP rules. Staff awareness training.
7 | AI-DAT-004 | AI tool supplier uses submitted data to train its models | Submitted Data | Data used for model training without consent | Proprietary or personal data incorporated into third-party AI models. GDPR risk. IP loss. | CIA | Terms of service not reviewed for all tools in use | 4 | 4 | 16 | Critical | [AI Policy Owner] | Risk Reduction | Review terms of service for all sanctioned tools. Require enterprise tier or opt-out of training.
8 | AI-SUP-001 | AI tool suppliers not assessed before adoption | AI Supplier Management | Unknown supplier risk | Tools adopted with poor security posture, unfavourable data use terms, or inadequate controls. | CIA | General procurement process may exist but not AI-specific | 4 | 4 | 16 | Critical | [AI Policy Owner] | Risk Reduction | Implement AI Supplier Review Criteria. Apply to all new tools before approval.
9 | AI-SUP-002 | No data processing agreement (DPA) in place with AI suppliers handling personal data | Supplier Contracts | Uncontracted data processing | GDPR breach. ICO enforcement. No contractual recourse if supplier misuses data. | CIA | DPAs not in place for AI tools | 4 | 4 | 16 | Critical | [AI Policy Owner] | Risk Reduction | Identify all tools processing personal data. Obtain DPA or require enterprise plan.
10 | AI-TEC-001 | No technical blocking of unapproved AI tools at network or endpoint level | Network / Endpoint Controls | Unrestricted shadow AI access | Unapproved tools used freely. Policy unenforceable without technical guardrails. | CIA | General web filtering may exist but AI categories not included | 4 | 5 | 20 | Critical | [AI Policy Owner] | Risk Reduction | Configure web filtering to block unapproved AI tool domains. Maintain block list.
11 | AI-PRO-003 | AI outputs used in decision-making without human review | AI-Assisted Decisions | Unvalidated AI output acting as a decision | Errors or hallucinations in AI output lead to incorrect decisions. Potential liability. | IA | No output validation requirement defined | 4 | 4 | 16 | Critical | [AI Policy Owner] | Risk Reduction | AUP to require output validation. Define review steps for high-stakes workflows.
12 | AI-REG-001 | AI use creates undisclosed profiling or automated decision-making under GDPR | GDPR Compliance | GDPR Article 22 breach — automated decision-making | ICO enforcement. Individual rights claims. Requirement to redo decisions manually. | CIA | GDPR policies exist but AI-specific obligations not assessed | 5 | 3 | 15 | Major | [AI Policy Owner] | Risk Reduction | Assess AI use cases for automated decision-making. Complete DPIA where required.
13 | AI-STF-001 | Staff not aware of AI governance policies or their responsibilities | Staff Awareness | Uninformed policy breach | Staff breach policy through ignorance. Risks materialise that could have been prevented. | CIA | Policies drafted but not yet communicated | 3 | 4 | 12 | Major | [AI Policy Owner] | Risk Reduction | Communicate policies to all staff. Deliver AI awareness training. Confirm completion.
14 | AI-INC-001 | No defined AI incident response process | AI Incident Management | AI incident mishandled or not escalated appropriately | Delayed response. Regulatory notification missed. No audit trail of response actions. | CIA | General IR process may exist but AI not included | 4 | 3 | 12 | Major | [AI Policy Owner] | Risk Reduction | Update incident response process to cover AI incidents. Define escalation and notification path.
15 | AI-EMG-003 | Agentic AI deployed without specific controls | Agentic AI Systems | Autonomous AI actions causing unintended harm | Unintended data exposure, erroneous transactions, or system changes made autonomously. | CIA | Agentic AI not yet deployed but risk noted as capability grows | 5 | 2 | 10 | Major | [AI Policy Owner] | Risk Reduction | Require specific approval for any agentic AI use cases. Define human-in-the-loop requirements.
Sample register — 15 of 48 risks. Full register with residual scoring, ISO 42001 mapping, and treatment plans: hello@blackchili.co.uk ¦ blackchili.co.uk

## Scoring Guide
Risk Scoring Guide
Likelihood | Score | Description
Highly Probable | 5 | AI-related incident or misuse likely to occur within the next month given current controls
Probable | 4 | AI-related incident likely within the next 6 months without additional controls
Possible | 3 | AI-related incident could occur within the next 2 years
Unlikely | 2 | AI-related incident unlikely but not impossible within the next 5 years
Rare | 1 | AI-related incident highly unlikely — less than once in the next 10 years
Impact | Score | Description
Very High | 5 | Regulatory breach (GDPR, FCA, ICO action). Serious reputational damage. Material client data exposed. Legal liability.
High | 4 | Sensitive data exposed to unauthorised parties. Significant client or commercial impact. Regulatory enquiry likely.
Medium | 3 | Internal data exposed beyond authorised users. Operational disruption. Minor client impact. Reputational risk.
Low | 2 | Contained incident with no external exposure. Minor operational inconvenience.
Very Low | 1 | No material impact. Contained and resolved with minimal effort.
|  |  | Risk Rating | Score | Description
|  |  | Critical | 16+ | Immediate action required. Senior leadership sign-off needed to accept.
|  |  | Major | 10–15 | Urgent treatment required. Management review team authority to accept.
|  |  | Moderate | 5–9 | Treatment plan required. Management authority to accept.
|  |  | Minor | 1–4 | Risk may be accepted. Monitor at regular review.

## Dashboard
AI Risk Register — Dashboard
Total Risks | Critical | Major | Moderate | Minor
15 | 5 | 7 | 3 | 0
risks | risks | risks | risks | risks
Category | Total | Critical | Major | Moderate | Minor
Governance | 2 | 2 | 0 | 0 | 0
Shadow AI | 2 | 1 | 1 | 0 | 0
Data Handling | 3 | 2 | 1 | 0 | 0
Supplier | 2 | 1 | 1 | 0 | 0
Technical Controls | 1 | 1 | 0 | 0 | 0
Outputs & Prompts | 1 | 0 | 1 | 0 | 0
Regulatory | 1 | 1 | 0 | 0 | 0
Staff Awareness | 1 | 0 | 1 | 0 | 0
Incident Response | 1 | 0 | 1 | 0 | 0
Emerging Risk | 1 | 1 | 0 | 0 | 0
Sample edition — 15 risks shown. Full register (48 risks) available as part of Black Chili's AI Governance & Guardrails Design service. hello@blackchili.co.uk